## test flow
Sr. no | Facilities | Normal Test | Autoport Test | Asset scan test
1 | Auto Port Load | 0 | 1 | 0
2 | Asset code Scan | 0 | 0 | 1
3 | Sample/ Production | OFF | OFF | 1 | Sr. No | Facilities
4 | Leak Test (FRL) | 0/1 | 0/1 | 0/1 | 1 | Connector Visual | 0/1
5 | Harness availability |  |  |  | 2 | All Error | Yes/no
6 | Fisrt stage |  |  |  | 3 | All circuit | Yes/no
7 | Multi stage
8 | Component Test | 0/1 | 0/1 | 0/1
9 | Label Printing | 0/1 | 0/1 | 0/1
10 | Barcode Matching 1 | 0/1 | 0/1 | 0/1
11 | Barcode Matching 2 | 0/1 | 0/1 | 0/1
12 | Report Generation | 0/1 | 0/1 | 0/1
13 | Actuation
14 | Remove Harness
15 | Cutter
16 | Abort

## Facilities
Sr. No | Facility/Parameter | G2.0 | Version | Comment | Target Date
1 | Min I/O Points | 64 | 1.0 | Complete
2 | Max I/O Points | 7680 | 1.0 | Complete
3 | Diode testing | Yes | 1.2 | Need software update
4 | Resistance Testing | Yes | 1.2 | Need software update
5 | Capacitor Testing | Yes | 1.x | Need software update
6 | Relay Testing | Yes | 1.2 | need software update
3 | USB | Yes | 1.0 | Complete
4 | Locations | 128 | 1.0 | Complete
5 | Lable printing | Yes | 1.0 | Complete
6 | Barcode Scanning | Yes | 1.0 | Complete
7 | Check board | Yes | 1.0 | Complete
8 | External Start/Stop | Yes | 1.0 | Complete
9 | Shut down | Yes | 1.0 | Complete
14 | Rejection bin | Yes | 1.2 | Need software update
15 | All circuit mode | Yes | 1.1 | progress
10 | Program Stages | Yes | 1.0 | Complete
11 | Factory reset | Yes | 1.0 | Complete
12 | 24V Auxillary O/P | Yes | 1.0 | Complete
13 | Date/Time | Yes | 1.0 | Complete
14 | Remote Desktop | Yes | 1.0 | Complete
15 | Snubber for Relay | Yes | 1.0 | Complete
16 | Pass/Fail Indicators | Yes | 1.0 | Complete
17 | Q Mark | Yes | 1.0 | Complete
18 | Release | Yes | 1.0 | Complete
19 | Cutter | Yes | 1.0 | Complete
26 | Audio O/P | Yes | 1.x | Need software update
20 | Conector visual | Yes | 1.0 | Complete
21 | Auto part load | Yes | 1.0 | Complete
29 | Asset code scan | Yes | 1.1 | progress
30 | All error mode | Yes | 1.2 | Need software update
31 | Report generation | Yes | 1.2 | Need software update
32 | Splice visualization | Yes | 1.2 | Need software update
22 | Leak test | Yes | 1.0 | Complete
23 | Log Creation | Yes | 1.0 | Complete
35 | custom flow | Yes | 1.x | Need software update
36 | tester network | Yes | 1.x | Need software update
37 | tracebility | Yes | 1.x | Need software update
38 | production display | Yes | 1.x | Need software update
39 | external device | Yes | 1.x | Need software/hardware update
24 | Supervisor login | Yes | 1.0 | Complete
25 | On board learn | Yes | 1.0 | Complete
26 | Import cutting chart Learn | Yes | 1.0 | Complete
27 | USB browsing learn | Yes | 1.0 | Complete
28 | export production log | Yes | 1.0 | Complete
45 | Test report export | Yes | 1.2 | Need software update
46 | Shift timing | Yes | 1.2 | Need software update
29 | Export database | Yes | 1.0 | Complete
48 | Grid view | Yes | 1.1 | progress
49 | custom operation message | Yes | 1.2 | Need software update
50 | raspberry pi power backup | Yes | 1.x | Need hardware update
51 | Final .exe preparation | yes | 1.x | Need software update